## Dev
Name | Developer Profile | Scrum Team | Bounded Context
Anton Easterday | Solid | A | Doctor
Beau Hockensmith | Mediocre | A | Doctor
Bruno Studley | New | A | Doctor
Craig Garlitz | New | A | Doctor
Francisco Hoppe | Star | A | Patient
Glenna Mcghie | Mediocre | A | Patient
Gregorio Darr | QA | A | Patient
Heriberto Martini | Solid | A | Patient
Hyun Jaffe | Mediocre | B | Ministry of Health
Isaura Casterline | New | B | Ministry of Health
Jacinto Immel | Mediocre | B | Ministry of Health
Jesse Kellogg | Solid | B | Ministry of Health
Josh Rusher | QA | B | Ministry of Health
Lashaunda Greaves | New | B | Ministry of Health
Lonnie Belz | Mediocre | C | Hospital Administration
Lorriane Demmer | Star | C | Hospital Administration
Margorie Beringer | Solid | C | Hospital Administration
Marquis Tefft | QA | C | Hospital Administration
Mckenzie Ma | Solid | C | Hospital Administration
Mervin Lindsay | Mediocre | C | Hospital Administration
Milan Hinman | Mediocre | C | Hospital Administration
Mohammad Tineo | Mediocre | D | Insurance
Nohemi Santini | New | D | Insurance
Olevia Haymaker | Mediocre | D | Insurance
Pedro Sisk | Solid | D | Insurance
Percy Aumiller | Mediocre | D | Insurance
Randy Pettitt | QA | D | Insurance
Renee Audette | Mediocre | D | Insurance
Teddy Straley | New | D | Insurance
Tyrone Goo | Mediocre | D | Insurance

## PMs
PM | Bounded Context | Spec Quality (5 is best)
Edgar Hibbler | Patient | 2
Sherlyn Cordle | Doctor | 3
Spencer Venezia | Ministry of Health | 1
Jamie Addington | Hospital Administration | 2
Georgine Roan | Insurance | 5

## User Stories count
Sprint duration: | 2 weeks
GA Cycle: | Actual: 9 months (39 weeks) |  |  |  | Predicted: | 5 months (22 weeks)
Go-Live: | We'll see based on the stabilization difficulties/ bugs. |  |  |  | Predicted: 5 weeks (~25% of the time it takes to go the GA Cycle)
User stories: | Assume a predited GA Cycle of 5 months, or 22 weeks
That means: 11 sprints
Assume each team pursues 3 user stories per sprint
There are 4 teams.
|  |  | Therefore, need these many user stories: |  | 132
Generation of time: | For each sprint, developers get a workload based on:
User stories agreed for that sprint
Minus time to re-work the problems from the past
Minus time to finish user stories not yet finished
Generation of bugs: | In GA: | Based on 3 factors: |  |  | Weight | Cost to fix
|  |  | Seniority of developer |  | 40% | 1
|  |  | Quality of PM spec |  | 30% | 3 | Initial problems of bad specs emerge in amount of time it takes to close a user story
|  |  | Code structure "spaghetti" factor |  | 30% | 2 | Dependencies that break - unit-testing style, not the stabilization issues that will happen
|  | "Mean" for a good team: |  | Bugs in each sprint should introduce 20% (sigma) delay to prediction. So a "good" team would delier in 26.4 weeks (instead of predicted 22, or actual 39)
| In Go-live: | Based on same 3 factors, but different weights
|  |  | Seniority of developer |  | 10% | 3
|  |  | Quality of PM spec |  | 50% | 6 | Bad specs really get noticed here, as client rejects
|  |  | Code structure "spaghetti" factor |  | 40% | 10 | Stabilization problems emerge here
Mean for a good team:

## Code Structure
Product is old.
Assume 20,000 Java classes |  |  | Call them D1, … D1500 for doctor, P1, …, P1200 for patient, etc.
For this project, only 4,000 will be touched, say. (kind of like rewriting 25% of the app - so in 4 releases you would "re-do" the app).
They are imperfectly broken into the bounded contexts
Each file mostly has to do with a bounded context
But, quite a few files include stuff from multiple bounded contexts.
Relationships across the files:
File1 calls File2
Any other worth adding?
How should brittleness be modeled?
How to represent file relationships that might cause things to break, whereas others do not?
Need a model of the probability that changing file F1 would lead to breaking files F34, F56, ….
How to model "common classes" that everyone balls, and are not a problem?
How to model "how deep the calling sequence"? Maybe limit it to a max of 20 calls in a stack trace?