## (Platform) ECS IaaS
Task Name | Status | Due Date | Members | URL
Burn In | Backlog |  | None | https://trello.com/c/1hGXzGsW/24-burn-in

## (Client) Cloud Security Infrastructure
Task Name | Status | Due Date | Members | URL
LinOTP redundancy & Scaling | Backlog | 2017-09-29T10:00:00.000Z | Tebogo Mokoena Gareth Hopkins Paul Stevens Kevin Coetzee | https://trello.com/c/9EdZUftC/2-linotp-redundancy-scaling

## (Platform) GabbaNet™
Task Name | Status | Due Date | Members | URL

## (Core) Infrastructure
Task Name | Status | Due Date | Members | URL
P2V Mailbox server | Impeded | 2017-07-03T15:00:00.000Z | 58c15ef789d680d711da74fd Andries Burger | https://trello.com/c/3VHTbTXd/23-p2v-mailbox-server

## (Client) oCIO
Task Name | Status | Due Date | Members | URL
Request IP details on GabbaNet™ | Completed | 2017-10-25T13:00:00.000Z | Gareth Hopkins | https://trello.com/c/m4BUzCUx/3-request-ip-details-on-gabbanet%E2%84%A2

## (Core) Skunk Works
Task Name | Status | Due Date | Members | URL

## (Platform) CVM
Task Name | Status | Due Date | Members | URL
Research ScaleIO as possible Ceph replacement. | Completed | 2017-11-14T13:00:00.000Z | Paul Stevens | https://trello.com/c/HYdDq5Pr/2-research-scaleio-as-possible-ceph-replacement

## (Platform) Database-as-a-Service
Task Name | Status | Due Date | Members | URL
Create MSTR databases on BRYPRDMSQL cluster (CRQ68239). | Completed | 2017-11-02T10:00:00.000Z | Carl Herbst | https://trello.com/c/eWtxvc7w/5-create-mstr-databases-on-bryprdmsql-cluster-crq68239

## (Client) Software Engineering
Task Name | Status | Due Date | Members | URL
Create a software installation play for Skywalker servers and run from the AWX server (ansible.platform.is) | In Progress | 2017-11-30T10:00:00.000Z | Paul Stevens | https://trello.com/c/V9MUAmtC/16-create-a-software-installation-play-for-skywalker-servers-and-run-from-the-awx-server-ansibleplatformis

## (Client) NetOps
Task Name | Status | Due Date | Members | URL
ran.isnet.net rebuild | Backlog |  | Gareth Hopkins | https://trello.com/c/JDvsJLY9/2-ranisnetnet-rebuild

## (Platform) Proxy-as-a-Service
Task Name | Status | Due Date | Members | URL
HA Proxy as a Service | Backlog |  | Gareth Hopkins | https://trello.com/c/qh1ANTyw/1-ha-proxy-as-a-service

## (Client) Marketing
Task Name | Status | Due Date | Members | URL
Load Balancing and CICD discussion | Backlog |  | Philani Paul Stevens | https://trello.com/c/rIl7UWDa/1-load-balancing-and-cicd-discussion

## (Client) Risk
Task Name | Status | Due Date | Members | URL
Risk Onboarding | Completed | 2017-11-21T10:00:00.000Z | Gareth Hopkins Paul Stevens Kevin Coetzee | https://trello.com/c/kMAb3KAK/1-risk-onboarding

## Patch Cycles
Task Name | Status | Due Date | Members | URL

## (1) Card Templates
Task Name | Status | Due Date | Members | URL
Create Ansible Play to [deploy feature] | Automation |  | None | https://trello.com/c/xGqfoHD5/8-create-ansible-play-to-deploy-feature

## (Client) CAM Team
Task Name | Status | Due Date | Members | URL
Request external FW changes from CSI to allow new servers access to services. | Backlog |  | None | https://trello.com/c/O3689TwL/4-request-external-fw-changes-from-csi-to-allow-new-servers-access-to-services

## (3) Backlog
Task Name | Status | Due Date | Members | URL
Microstrategy Production | Medium Priority |  | None | https://trello.com/c/oMLmPiId/72-microstrategy-production

## (Platform) Systems Centre Operations Manager
Task Name | Status | Due Date | Members | URL
Configure administration setting for automatic alert resolution | Backlog |  | None | https://trello.com/c/BZWSfwx0/16-configure-administration-setting-for-automatic-alert-resolution

## (Platform) Elastic-as-a-Service
Task Name | Status | Due Date | Members | URL
Add servers to Skaduwee | Backlog | 2017-11-03T14:00:00.000Z | Kevinesan Pillay Andries Burger | https://trello.com/c/JyZc1b48/8-add-servers-to-skaduwee

## (Client) MWeb
Task Name | Status | Due Date | Members | URL
MWEB onboarding | Backlog |  | None | https://trello.com/c/W3VnwJ3Z/1-mweb-onboarding

## (Client) OSS
Task Name | Status | Due Date | Members | URL
JBoss Phase 2 | Backlog |  | None | https://trello.com/c/VX5wv8FO/6-jboss-phase-2

## (Core) Dev Projects
Task Name | Status | Due Date | Members | URL
Trelloreporter 0.1.0 | Completed | 2017-11-10T13:00:00.000Z | Philani Paul Stevens | https://trello.com/c/lrJVXuKH/1-trelloreporter-010

## (Client) Broadband Operations
Task Name | Status | Due Date | Members | URL
[Stage] Postgres server for AlwaysOn Development | Backlog |  | None | https://trello.com/c/AWHeEd6W/1-stage-postgres-server-for-alwayson-development

## (Platform) ECS PaaS (OpenShift)
Task Name | Status | Due Date | Members | URL
Build 1 x deploy node on ECS Lab | Completed | 2017-12-01T10:00:00.000Z | Wayne Coetzee | https://trello.com/c/FxSv5yq9/4-build-1-x-deploy-node-on-ecs-lab

## Projects
Task Name | Status | Due Date | Members | URL
Change Control process | Completed | 2017-06-09T19:00:00.000Z | Paul Stevens | https://trello.com/c/kv6iQITt/100-change-control-process

## (Client) Ignite
Task Name | Status | Due Date | Members | URL
[STAGE] Deploy new CentOS 7 App01 Host | Completed | 2017-11-03T08:00:00.000Z | Tebogo Mokoena | https://trello.com/c/5hGOtKof/3-stage-deploy-new-centos-7-app01-host

## (Platform) Monitoring-as-a-Service
Task Name | Status | Due Date | Members | URL