## (Platform) ECS PaaS (OpenShift)
Task Name | Status | Due Date | Members | URL
Build 4 x worker nodes on ECS Lab | Completed | 2017-12-01T10:00:00.000Z | Wayne Coetzee | https://trello.com/c/VTwUlfPr/3-build-4-x-worker-nodes-on-ecs-lab

## (Platform) Database-as-a-Servic
Task Name | Status | Due Date | Members | URL
Create MSTR databases on BRYPRDMSQL cluster (CRQ68239). | Completed | 2017-11-02T10:00:00.000Z | Carl Herbst | https://trello.com/c/eWtxvc7w/5-create-mstr-databases-on-bryprdmsql-cluster-crq68239

## (Platform) Monitoring-as-a-Serv
Task Name | Status | Due Date | Members | URL

## (3) Backlog
Task Name | Status | Due Date | Members | URL
MySQL Redesign | Medium Priority |  | None | https://trello.com/c/biloCAhu/11-mysql-redesign

## (Platform) CVM
Task Name | Status | Due Date | Members | URL
Build a bill of materials for new CVM deployment | Completed | 2017-11-14T13:00:00.000Z | Paul Stevens | https://trello.com/c/DK8BDUkr/1-build-a-bill-of-materials-for-new-cvm-deployment

## (Client) Cloud Security Infrast
Task Name | Status | Due Date | Members | URL
CSI Syslog Server upgrades | Backlog | 2017-09-29T13:00:00.000Z | Tebogo Mokoena 58c15ef789d680d711da74fd Emanuel Muza | https://trello.com/c/gEGnDfd5/3-csi-syslog-server-upgrades

## (Client) Broadband Operations
Task Name | Status | Due Date | Members | URL
[Stage] Postgres server for AlwaysOn Development | Backlog |  | None | https://trello.com/c/AWHeEd6W/1-stage-postgres-server-for-alwayson-development

## (Client) MWeb
Task Name | Status | Due Date | Members | URL
MWEB onboarding | Backlog |  | None | https://trello.com/c/W3VnwJ3Z/1-mweb-onboarding

## (Platform) GabbaNet™
Task Name | Status | Due Date | Members | URL

## (Core) Skunk Works
Task Name | Status | Due Date | Members | URL

## (Platform) Systems Centre Opera
Task Name | Status | Due Date | Members | URL
Import management packs | Backlog |  | None | https://trello.com/c/UtAN1jsx/21-import-management-packs

## (Platform) Elastic-as-a-Service
Task Name | Status | Due Date | Members | URL
Document all testing done for the enviroment | In Progress | 2017-11-17T10:00:00.000Z | None | https://trello.com/c/knPYK0Vg/38-document-all-testing-done-for-the-enviroment

## Projects
Task Name | Status | Due Date | Members | URL
OpenLDAP Proxy Auth (GitLab) | Completed | 2017-09-01T13:00:00.000Z | Wayne Coetzee Paul Stevens | https://trello.com/c/XatlbCXw/129-openldap-proxy-auth-gitlab

## (Client) CAM Team
Task Name | Status | Due Date | Members | URL
Configure 5K's to uplink to GabbNet™ | Backlog |  | None | https://trello.com/c/1NboBCvr/11-configure-5ks-to-uplink-to-gabbnet%E2%84%A2

## (Client) Ignite
Task Name | Status | Due Date | Members | URL
Migrate Ignite apps from web01 to new Ignite servers | In Progress | 2017-12-05T10:00:00.000Z | Tebogo Mokoena | https://trello.com/c/05lJd7I3/15-migrate-ignite-apps-from-web01-to-new-ignite-servers

## (1) Card Templates
Task Name | Status | Due Date | Members | URL
Migrate [service] for [client] | New Service |  | None | https://trello.com/c/cl9gXmiD/15-migrate-service-for-client

## Patch Cycles
Task Name | Status | Due Date | Members | URL

## (Platform) ECS IaaS
Task Name | Status | Due Date | Members | URL
Deploy new Ubuntu 16.04LTS Host for ECS Lab | Completed | 2017-11-08T13:00:00.000Z | Wayne Coetzee | https://trello.com/c/kbnwsU9x/5-deploy-new-ubuntu-1604lts-host-for-ecs-lab

## (Client) OSS
Task Name | Status | Due Date | Members | URL
VM's for Netcool Test Environment | Backlog |  | None | https://trello.com/c/o1RPB5tn/7-vms-for-netcool-test-environment

## (Client) Software Engineering
Task Name | Status | Due Date | Members | URL
CZ - Implement a backup scheme that truncates transaction logs. | Completed | 2017-11-01T14:00:00.000Z | Brian Francois Prinsloo Carl Herbst | https://trello.com/c/o9bG7n92/1-cz-implement-a-backup-scheme-that-truncates-transaction-logs

## (Client) NetOps
Task Name | Status | Due Date | Members | URL
ran.isnet.net rebuild | Backlog |  | Gareth Hopkins | https://trello.com/c/JDvsJLY9/2-ranisnetnet-rebuild

## (Client) Risk
Task Name | Status | Due Date | Members | URL
Risk Onboarding | Completed | 2017-11-21T10:00:00.000Z | Paul Stevens Gareth Hopkins Kevin Coetzee | https://trello.com/c/kMAb3KAK/1-risk-onboarding

## (Client) oCIO
Task Name | Status | Due Date | Members | URL
Informatica Production Server | Backlog |  | None | https://trello.com/c/PTMhGgEm/23-informatica-production-server

## (Core) Infrastructure
Task Name | Status | Due Date | Members | URL
Authoritative Name Server Replacement | Backlog |  | None | https://trello.com/c/dbeuk4kV/43-authoritative-name-server-replacement

## (Platform) Proxy-as-a-Service
Task Name | Status | Due Date | Members | URL
HA Proxy as a Service | Backlog |  | Gareth Hopkins | https://trello.com/c/qh1ANTyw/1-ha-proxy-as-a-service

## (Core) Dev Projects
Task Name | Status | Due Date | Members | URL
Trelloreporter 0.1.0 | Completed | 2017-11-10T13:00:00.000Z | Paul Stevens Philani | https://trello.com/c/lrJVXuKH/1-trelloreporter-010

## (Client) Marketing
Task Name | Status | Due Date | Members | URL
Load Balancing and CICD discussion | Backlog |  | Paul Stevens Philani | https://trello.com/c/rIl7UWDa/1-load-balancing-and-cicd-discussion