## (Client) OSS
Task Name | Status | Due Date | Members | URL
Deploy new Ubuntu 16.04 Virtual Host | Backlog |  | None | https://trello.com/c/h1qVD4fY/3-deploy-new-ubuntu-1604-virtual-host

## (Platform) Database-as-a-Servic
Task Name | Status | Due Date | Members | URL
Test PROD MSQL service accounts for Bitanium for the MSTR databases | Completed | 2017-11-13T10:00:00.000Z | Carl Herbst | https://trello.com/c/ZjKI70ua/8-test-prod-msql-service-accounts-for-bitanium-for-the-mstr-databases

## (Platform) Elastic-as-a-Service
Task Name | Status | Due Date | Members | URL
Create systemd units for kafka components startup | Completed | 2017-11-17T10:00:00.000Z | Kevinesan Pillay Andries Burger | https://trello.com/c/yENFtZta/30-create-systemd-units-for-kafka-components-startup

## (Client) Broadband Operations
Task Name | Status | Due Date | Members | URL
[Stage] Postgres server for AlwaysOn Development | Backlog |  | None | https://trello.com/c/AWHeEd6W/1-stage-postgres-server-for-alwayson-development

## (Client) Cloud Security Infrast
Task Name | Status | Due Date | Members | URL
LinOTP redundancy & Scaling | Backlog | 2017-09-29T10:00:00.000Z | Gareth Hopkins Tebogo Mokoena Kevin Coetzee Paul Stevens | https://trello.com/c/9EdZUftC/2-linotp-redundancy-scaling

## Patch Cycles
Task Name | Status | Due Date | Members | URL

## (Client) oCIO
Task Name | Status | Due Date | Members | URL
[Stage] Deploy new Hubble Web Server | In Progress | 2017-11-27T13:00:00.000Z | Francois Prinsloo Brian | https://trello.com/c/u5DgY9YH/26-stage-deploy-new-hubble-web-server

## (Client) Software Engineering
Task Name | Status | Due Date | Members | URL
X-Frame-Options header in IIS | Backlog |  | Francois Prinsloo Brian | https://trello.com/c/atz3sVu3/20-x-frame-options-header-in-iis

## (Client) Risk
Task Name | Status | Due Date | Members | URL
Risk Onboarding | Completed | 2017-11-21T10:00:00.000Z | Gareth Hopkins Kevin Coetzee Paul Stevens | https://trello.com/c/kMAb3KAK/1-risk-onboarding

## (Platform) CVM
Task Name | Status | Due Date | Members | URL
Research ScaleIO as possible Ceph replacement. | Completed | 2017-11-14T13:00:00.000Z | Paul Stevens | https://trello.com/c/HYdDq5Pr/2-research-scaleio-as-possible-ceph-replacement

## (Client) CAM Team
Task Name | Status | Due Date | Members | URL
Check original scripts and applications on current Util 2 | Backlog |  | None | https://trello.com/c/ooASFBPc/3-check-original-scripts-and-applications-on-current-util-2

## (1) Card Templates
Task Name | Status | Due Date | Members | URL
Build [service] to enable [feature] | New Service |  | None | https://trello.com/c/7TnyKDwc/13-build-service-to-enable-feature

## Projects
Task Name | Status | Due Date | Members | URL
Web Proxy Redesign | Conceptual |  | None | https://trello.com/c/F3jZXFOb/14-web-proxy-redesign

## (Core) Skunk Works
Task Name | Status | Due Date | Members | URL

## (Platform) ECS PaaS (OpenShift)
Task Name | Status | Due Date | Members | URL
Deploy OpenShift Origin 3.6 according to deployment docs and notes | In Progress | 2017-12-15T10:00:00.000Z | Wayne Coetzee | https://trello.com/c/mpjKv3BE/5-deploy-openshift-origin-36-according-to-deployment-docs-and-notes

## (Core) Dev Projects
Task Name | Status | Due Date | Members | URL
Trelloreporter 0.1.0 | Completed | 2017-11-10T13:00:00.000Z | Philani Paul Stevens | https://trello.com/c/lrJVXuKH/1-trelloreporter-010

## (Platform) Proxy-as-a-Service
Task Name | Status | Due Date | Members | URL
HA Proxy as a Service | Backlog |  | Gareth Hopkins | https://trello.com/c/qh1ANTyw/1-ha-proxy-as-a-service

## (Platform) Systems Centre Opera
Task Name | Status | Due Date | Members | URL
Deploy SCOM 2016 Servers | In Progress | 2017-11-20T13:00:00.000Z | Francois Prinsloo Brian | https://trello.com/c/6NwuoQax/4-deploy-scom-2016-servers

## (Core) Infrastructure
Task Name | Status | Due Date | Members | URL
FTP Service Redesign | Backlog |  | None | https://trello.com/c/heMFX0xr/50-ftp-service-redesign

## (Platform) ECS IaaS
Task Name | Status | Due Date | Members | URL
Rebuild 3. Use temp NFS storage. | Completed | 2017-11-08T13:00:00.000Z | Andries Burger | https://trello.com/c/luMkXeH7/27-rebuild-3-use-temp-nfs-storage

## (Client) MWeb
Task Name | Status | Due Date | Members | URL
MWEB onboarding | Backlog |  | None | https://trello.com/c/W3VnwJ3Z/1-mweb-onboarding

## (Client) NetOps
Task Name | Status | Due Date | Members | URL
ran.isnet.net rebuild | Backlog |  | Gareth Hopkins | https://trello.com/c/JDvsJLY9/2-ranisnetnet-rebuild

## (Platform) GabbaNet™
Task Name | Status | Due Date | Members | URL

## (Platform) Monitoring-as-a-Serv
Task Name | Status | Due Date | Members | URL

## (Client) Ignite
Task Name | Status | Due Date | Members | URL
Import SSL wildcard certificate for all Ignite sites | In Progress | 2017-12-05T13:00:00.000Z | Tebogo Mokoena | https://trello.com/c/Afvt02Mp/20-import-ssl-wildcard-certificate-for-all-ignite-sites

## (Client) Marketing
Task Name | Status | Due Date | Members | URL
Load Balancing and CICD discussion | Backlog |  | Philani Paul Stevens | https://trello.com/c/rIl7UWDa/1-load-balancing-and-cicd-discussion

## (3) Backlog
Task Name | Status | Due Date | Members | URL
Web Proxy Redesign | Low Priority |  | None | https://trello.com/c/R7QUeqZH/13-web-proxy-redesign