## (Core) Skunk Works
Task Name | Status | Due Date | Members | URL

## (Client) CAM Team
Task Name | Status | Due Date | Members | URL
Configure 5K's to uplink to GabbNet™ | Backlog |  | None | https://trello.com/c/1NboBCvr/11-configure-5ks-to-uplink-to-gabbnet%E2%84%A2

## (Platform) CVM
Task Name | Status | Due Date | Members | URL
Retrieve "shared storage" hardware from Randview DC. | Backlog |  | None | https://trello.com/c/wGGO98jc/3-retrieve-shared-storage-hardware-from-randview-dc

## (Core) Dev Projects
Task Name | Status | Due Date | Members | URL
Trelloreporter 1.0.0 | In Progress | 2017-12-08T13:00:00.000Z | Paul Stevens Philani | https://trello.com/c/fRDPTsrb/4-trelloreporter-100

## (Client) Ignite
Task Name | Status | Due Date | Members | URL
Get MySQL dump data of existing Ignite databases and write to MySQL DbaaS databases | In Progress | 2017-12-04T10:00:00.000Z | Nondi | https://trello.com/c/I6UpTFo1/17-get-mysql-dump-data-of-existing-ignite-databases-and-write-to-mysql-dbaas-databases

## (Platform) Database-as-a-Servic
Task Name | Status | Due Date | Members | URL
Increase disk space on MSQL DBaaS cluster. | Completed | 2017-11-06T10:00:00.000Z | Carl Herbst Brian | https://trello.com/c/G6ea4Zqc/4-increase-disk-space-on-msql-dbaas-cluster

## (Client) Marketing
Task Name | Status | Due Date | Members | URL
Load Balancing and CICD discussion | Backlog |  | Paul Stevens Philani | https://trello.com/c/rIl7UWDa/1-load-balancing-and-cicd-discussion

## Patch Cycles
Task Name | Status | Due Date | Members | URL

## (Client) oCIO
Task Name | Status | Due Date | Members | URL
[TEST] Deploy new Siebel App1 VM | Completed | 2017-11-08T10:00:00.000Z | Brian Francois Prinsloo | https://trello.com/c/0gSxEkbk/7-test-deploy-new-siebel-app1-vm

## (Platform) ECS PaaS (OpenShift)
Task Name | Status | Due Date | Members | URL
Build 4 x worker nodes on ECS Lab | Completed | 2017-12-01T10:00:00.000Z | Wayne Coetzee | https://trello.com/c/VTwUlfPr/3-build-4-x-worker-nodes-on-ecs-lab

## (Platform) ECS IaaS
Task Name | Status | Due Date | Members | URL
ECS Kenya Deployment | Backlog |  | None | https://trello.com/c/NwMrSP00/30-ecs-kenya-deployment

## (Platform) Monitoring-as-a-Serv
Task Name | Status | Due Date | Members | URL

## (Client) OSS
Task Name | Status | Due Date | Members | URL
Check implications of DB2 licensing on running a test-DB | Backlog |  | None | https://trello.com/c/Vr4qVlUj/5-check-implications-of-db2-licensing-on-running-a-test-db

## (Core) Infrastructure
Task Name | Status | Due Date | Members | URL
PKL - whole.is.co.za E2111 DIMM 1 error | Backlog |  | None | https://trello.com/c/tya7qb8c/63-pkl-wholeiscoza-e2111-dimm-1-error

## (3) Backlog
Task Name | Status | Due Date | Members | URL
Microstrategy Production | Medium Priority |  | None | https://trello.com/c/oMLmPiId/72-microstrategy-production

## (Client) NetOps
Task Name | Status | Due Date | Members | URL
ran.isnet.net rebuild | Backlog |  | Gareth Hopkins | https://trello.com/c/JDvsJLY9/2-ranisnetnet-rebuild

## (Platform) Systems Centre Opera
Task Name | Status | Due Date | Members | URL
Backup unsealed management packs | Backlog |  | None | https://trello.com/c/sECCqJrG/19-backup-unsealed-management-packs

## (Client) Cloud Security Infrast
Task Name | Status | Due Date | Members | URL
LinOTP redundancy & Scaling | Backlog | 2017-09-29T10:00:00.000Z | Paul Stevens Kevin Coetzee Tebogo Mokoena Gareth Hopkins | https://trello.com/c/9EdZUftC/2-linotp-redundancy-scaling

## (Platform) Elastic-as-a-Service
Task Name | Status | Due Date | Members | URL
Test Filebeat - Kafka - Logstash - Elastic - Kibana stack | Completed | 2017-11-14T10:00:00.000Z | Kevinesan Pillay Andries Burger | https://trello.com/c/opxtlMZX/27-test-filebeat-kafka-logstash-elastic-kibana-stack

## (Platform) Proxy-as-a-Service
Task Name | Status | Due Date | Members | URL
HA Proxy as a Service | Backlog |  | Gareth Hopkins | https://trello.com/c/qh1ANTyw/1-ha-proxy-as-a-service

## (1) Card Templates
Task Name | Status | Due Date | Members | URL
Deploy new Windows Virtual Host | Server Build |  | None | https://trello.com/c/F9FiKMCN/4-deploy-new-windows-virtual-host

## Projects
Task Name | Status | Due Date | Members | URL
AlwaysOn Web Development | Completed | 2017-10-12T10:00:00.000Z | Brian Francois Prinsloo Gareth Hopkins | https://trello.com/c/iOYjHMOv/83-alwayson-web-development

## (Client) Broadband Operations
Task Name | Status | Due Date | Members | URL
[Stage] Postgres server for AlwaysOn Development | Backlog |  | None | https://trello.com/c/AWHeEd6W/1-stage-postgres-server-for-alwayson-development

## (Platform) GabbaNet™
Task Name | Status | Due Date | Members | URL

## (Client) Risk
Task Name | Status | Due Date | Members | URL
Risk Onboarding | Completed | 2017-11-21T10:00:00.000Z | Paul Stevens Kevin Coetzee Gareth Hopkins | https://trello.com/c/kMAb3KAK/1-risk-onboarding

## (Client) Software Engineering
Task Name | Status | Due Date | Members | URL
CICD process for release management | Backlog |  | Paul Stevens Philani | https://trello.com/c/5kYYQf9A/10-cicd-process-for-release-management

## (Client) MWeb
Task Name | Status | Due Date | Members | URL
MWEB onboarding | Backlog |  | None | https://trello.com/c/W3VnwJ3Z/1-mweb-onboarding