## (Client) Risk
Task Name | Status | Due Date | Members | URL
Risk Onboarding | Completed | 2017-11-21T10:00:00.000Z | Kevin Coetzee Paul Stevens Gareth Hopkins | https://trello.com/c/kMAb3KAK/1-risk-onboarding

## (Client) Broadband Operations
Task Name | Status | Due Date | Members | URL
[Stage] Postgres server for AlwaysOn Development | Backlog |  | None | https://trello.com/c/AWHeEd6W/1-stage-postgres-server-for-alwayson-development

## (Platform) Elastic-as-a-Service
Task Name | Status | Due Date | Members | URL
Complete required Ansible plays | In Progress | 2017-11-24T10:00:00.000Z | None | https://trello.com/c/f0e2J3xQ/39-complete-required-ansible-plays

## (Platform) Systems Centre Opera
Task Name | Status | Due Date | Members | URL
Set the Operations Manager Administrators user role | Backlog |  | None | https://trello.com/c/XXVomY4X/7-set-the-operations-manager-administrators-user-role

## (Platform) Monitoring-as-a-Serv
Task Name | Status | Due Date | Members | URL

## (Platform) ECS PaaS (OpenShift)
Task Name | Status | Due Date | Members | URL
Deploy Jenkins containers to manage pipelines for OSS and Platform Engineering deployments | Backlog |  | None | https://trello.com/c/MwtJUFbo/6-deploy-jenkins-containers-to-manage-pipelines-for-oss-and-platform-engineering-deployments

## Projects
Task Name | Status | Due Date | Members | URL
URM nologin/Ansible play for Bastion hosts | Completed | 2017-09-04T10:00:00.000Z | Wayne Coetzee | https://trello.com/c/snXuKZ5w/130-urm-nologin-ansible-play-for-bastion-hosts

## (Platform) ECS IaaS
Task Name | Status | Due Date | Members | URL
Deploy AIO ECS cluster on Stage box | Backlog |  | Wayne Coetzee Kevin Coetzee | https://trello.com/c/7TfCv5OQ/17-deploy-aio-ecs-cluster-on-stage-box

## (Client) Software Engineering
Task Name | Status | Due Date | Members | URL
Commercial Portal release | Backlog | 2017-12-08T08:00:00.000Z | Philani Paul Stevens Brian Gareth Hopkins Carl Herbst | https://trello.com/c/zOZx7vuf/7-commercial-portal-release

## (Client) CAM Team
Task Name | Status | Due Date | Members | URL
Request external FW changes from CSI to allow new servers access to services. | Backlog |  | None | https://trello.com/c/O3689TwL/4-request-external-fw-changes-from-csi-to-allow-new-servers-access-to-services

## (Client) NetOps
Task Name | Status | Due Date | Members | URL
ran.isnet.net rebuild | Backlog |  | Gareth Hopkins | https://trello.com/c/JDvsJLY9/2-ranisnetnet-rebuild

## (Platform) GabbaNet™
Task Name | Status | Due Date | Members | URL

## (Client) Marketing
Task Name | Status | Due Date | Members | URL
Load Balancing and CICD discussion | Backlog |  | Philani Paul Stevens | https://trello.com/c/rIl7UWDa/1-load-balancing-and-cicd-discussion

## (Platform) Database-as-a-Servic
Task Name | Status | Due Date | Members | URL
Increase disk space on MSQL DBaaS cluster. | Completed | 2017-11-06T10:00:00.000Z | Brian Carl Herbst | https://trello.com/c/G6ea4Zqc/4-increase-disk-space-on-msql-dbaas-cluster

## (Core) Dev Projects
Task Name | Status | Due Date | Members | URL
Trelloreporter 1.0.0 | In Progress | 2017-12-08T13:00:00.000Z | Philani Paul Stevens | https://trello.com/c/fRDPTsrb/4-trelloreporter-100

## (Client) Cloud Security Infrast
Task Name | Status | Due Date | Members | URL
LinOTP redundancy & Scaling | Backlog | 2017-09-29T10:00:00.000Z | Tebogo Mokoena Paul Stevens Gareth Hopkins Kevin Coetzee | https://trello.com/c/9EdZUftC/2-linotp-redundancy-scaling

## (Client) Ignite
Task Name | Status | Due Date | Members | URL
[STAGE] Deploy new CentOS 7 Worker02 Host | Completed | 2017-11-03T08:00:00.000Z | Tebogo Mokoena | https://trello.com/c/DLytSrlr/6-stage-deploy-new-centos-7-worker02-host

## (Core) Skunk Works
Task Name | Status | Due Date | Members | URL

## (Core) Infrastructure
Task Name | Status | Due Date | Members | URL
Add additional 200GB LUN to fenix-mgr-pkl-01 (CRQ68248) | Completed | 2017-11-03T08:00:00.000Z | Kevin Coetzee | https://trello.com/c/lCsN88Fd/5-add-additional-200gb-lun-to-fenix-mgr-pkl-01-crq68248

## (Platform) Proxy-as-a-Service
Task Name | Status | Due Date | Members | URL
HA Proxy as a Service | Backlog |  | Gareth Hopkins | https://trello.com/c/qh1ANTyw/1-ha-proxy-as-a-service

## (Client) OSS
Task Name | Status | Due Date | Members | URL
websvc.ipsa.is.co.za vm move to Bry IPSA Lab. | Backlog |  | 58c15ef789d680d711da74fd Francois Prinsloo | https://trello.com/c/LXdQzJVW/8-websvcipsaiscoza-vm-move-to-bry-ipsa-lab

## (Platform) CVM
Task Name | Status | Due Date | Members | URL
Retrieve "shared storage" hardware from Randview DC. | Backlog |  | None | https://trello.com/c/wGGO98jc/3-retrieve-shared-storage-hardware-from-randview-dc

## (3) Backlog
Task Name | Status | Due Date | Members | URL
Monitoring System Replacement | Low Priority |  | None | https://trello.com/c/fIEKAmmN/16-monitoring-system-replacement

## (1) Card Templates
Task Name | Status | Due Date | Members | URL
Create Ansible Role for [feature] | Automation |  | None | https://trello.com/c/GIDbCs9w/7-create-ansible-role-for-feature

## (Client) oCIO
Task Name | Status | Due Date | Members | URL
Deploy new Hubble Application Server | Completed | 2017-11-21T13:00:00.000Z | Tebogo Mokoena | https://trello.com/c/EVfjVE4G/17-deploy-new-hubble-application-server

## (Client) MWeb
Task Name | Status | Due Date | Members | URL
MWEB onboarding | Backlog |  | None | https://trello.com/c/W3VnwJ3Z/1-mweb-onboarding

## Patch Cycles
Task Name | Status | Due Date | Members | URL