## (Platform) Elastic-as-a-Service
Task Name | Status | Due Date | Members | URL
Install Elastic virtual hosts | Completed |  | Andries Burger Kevinesan Pillay | https://trello.com/c/pY0VvMKR/12-install-elastic-virtual-hosts

## (Client) Risk
Task Name | Status | Due Date | Members | URL
Risk Onboarding | Completed | 2017-11-21T10:00:00.000Z | Kevin Coetzee Gareth Hopkins Paul Stevens | https://trello.com/c/kMAb3KAK/1-risk-onboarding

## (Platform) ECS PaaS (OpenShift)
Task Name | Status | Due Date | Members | URL
Deploy OpenShift Origin 3.6 according to deployment docs and notes | In Progress | 2017-12-15T10:00:00.000Z | Wayne Coetzee | https://trello.com/c/mpjKv3BE/5-deploy-openshift-origin-36-according-to-deployment-docs-and-notes

## (3) Backlog
Task Name | Status | Due Date | Members | URL
Authentication Upgrade | Low Priority |  | None | https://trello.com/c/ENY55Xoo/15-authentication-upgrade

## (Client) Broadband Operations
Task Name | Status | Due Date | Members | URL
[Stage] Postgres server for AlwaysOn Development | Backlog |  | None | https://trello.com/c/AWHeEd6W/1-stage-postgres-server-for-alwayson-development

## (Platform) Monitoring-as-a-Serv
Task Name | Status | Due Date | Members | URL

## (Client) Ignite
Task Name | Status | Due Date | Members | URL
[STAGE] Deploy new CentOS 7 Worker02 Host | Completed | 2017-11-03T08:00:00.000Z | Tebogo Mokoena | https://trello.com/c/DLytSrlr/6-stage-deploy-new-centos-7-worker02-host

## (Platform) Database-as-a-Servic
Task Name | Status | Due Date | Members | URL
Increase disk space on MSQL DBaaS cluster. | Completed | 2017-11-06T10:00:00.000Z | Brian Carl Herbst | https://trello.com/c/G6ea4Zqc/4-increase-disk-space-on-msql-dbaas-cluster

## (Client) MWeb
Task Name | Status | Due Date | Members | URL
MWEB onboarding | Backlog |  | None | https://trello.com/c/W3VnwJ3Z/1-mweb-onboarding

## (Client) Cloud Security Infrast
Task Name | Status | Due Date | Members | URL
CSI Syslog Server upgrades | Backlog | 2017-09-29T13:00:00.000Z | Tebogo Mokoena Emanuel Muza 58c15ef789d680d711da74fd | https://trello.com/c/gEGnDfd5/3-csi-syslog-server-upgrades

## Projects
Task Name | Status | Due Date | Members | URL
ASMR Onboarding DEV | Completed | 2017-06-09T10:00:00.000Z | Francois Prinsloo Gareth Hopkins Paul Stevens Brian 58c15ef789d680d711da74fd | https://trello.com/c/5hrQ9BvK/70-asmr-onboarding-dev

## (Platform) Systems Centre Opera
Task Name | Status | Due Date | Members | URL
Enable Agent Proxy as a default setting | Backlog |  | None | https://trello.com/c/bkfeweUu/14-enable-agent-proxy-as-a-default-setting

## (Platform) GabbaNet™
Task Name | Status | Due Date | Members | URL

## (Client) OSS
Task Name | Status | Due Date | Members | URL
IPSA Hyper-V Nodes Maintenance | Backlog | 2017-12-15T21:00:00.000Z | Brian Francois Prinsloo | https://trello.com/c/CUI6iLKv/10-ipsa-hyper-v-nodes-maintenance

## Patch Cycles
Task Name | Status | Due Date | Members | URL

## (1) Card Templates
Task Name | Status | Due Date | Members | URL
Create Ansible Role for [feature] | Automation |  | None | https://trello.com/c/GIDbCs9w/7-create-ansible-role-for-feature

## (Core) Dev Projects
Task Name | Status | Due Date | Members | URL
Trelloreporter 0.2.0 | Completed | 2017-11-17T13:00:00.000Z | Paul Stevens Philani | https://trello.com/c/mpROhzPG/2-trelloreporter-020

## (Client) Marketing
Task Name | Status | Due Date | Members | URL
Load Balancing and CICD discussion | Backlog |  | Paul Stevens Philani | https://trello.com/c/rIl7UWDa/1-load-balancing-and-cicd-discussion

## (Platform) Proxy-as-a-Service
Task Name | Status | Due Date | Members | URL
HA Proxy as a Service | Backlog |  | Gareth Hopkins | https://trello.com/c/qh1ANTyw/1-ha-proxy-as-a-service

## (Client) CAM Team
Task Name | Status | Due Date | Members | URL
Schedule shutdown of existing Util1 servers. | Backlog |  | None | https://trello.com/c/UmU2Vrpe/9-schedule-shutdown-of-existing-util1-servers

## (Core) Skunk Works
Task Name | Status | Due Date | Members | URL

## (Core) Infrastructure
Task Name | Status | Due Date | Members | URL
backup1-ke.services.is.co.za : Add Additional Space | Completed | 2017-10-17T10:00:00.000Z | Kevin Coetzee Brett Illing | https://trello.com/c/1A56iknK/30-backup1-keservicesiscoza-add-additional-space

## (Platform) ECS IaaS
Task Name | Status | Due Date | Members | URL
Investigate iSCSI connections to Acronis storage though Cinder | Backlog |  | None | https://trello.com/c/7MBIZg75/31-investigate-iscsi-connections-to-acronis-storage-though-cinder

## (Platform) CVM
Task Name | Status | Due Date | Members | URL
CVM Support Handover | Backlog |  | None | https://trello.com/c/uFPqiXSN/6-cvm-support-handover

## (Client) oCIO
Task Name | Status | Due Date | Members | URL
Microstrategy Production | Backlog |  | None | https://trello.com/c/0LTpNrRZ/22-microstrategy-production

## (Client) NetOps
Task Name | Status | Due Date | Members | URL
ran.isnet.net rebuild | Backlog |  | Gareth Hopkins | https://trello.com/c/JDvsJLY9/2-ranisnetnet-rebuild

## (Client) Software Engineering
Task Name | Status | Due Date | Members | URL
Upgrade CC- & CZ MSQL Cluster Nodes Specifications | Completed | 2017-11-17T13:00:00.000Z | Brian Francois Prinsloo Carl Herbst Gareth Hopkins Nondi | https://trello.com/c/y3KaZLkw/6-upgrade-cc-cz-msql-cluster-nodes-specifications